## Sheet1
Tomato	WEEK ->	-8	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
ACTIVITY
Buy Seed
Order Seedling
Mow
Till
Buy Fertilizer (Manure)
Fertilize (spread manure)
Rotovate
Build Beds
Set-up irrigation
Set-up ground cover-weed inhibitor

Start Seedling
Water Seedling
Treat Seedling

Transplant
Trim and Tie
Set-up Trellis/Cane
Weed
Spray Preventitive
Water (rain dependent)

Harvest (percentage of max weekly production (600grams) )																	10	15	30	60	80	100	100	80	60	30	10
Teardown